**Kent SACRE Agreed Syllabus Review**

**Project Plan 2016 - 2017**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Activity** | **Lead Responsibility / Involvement** | **Completion Date** |
| 1 | Secure funding to complete review and publish web based KAS | SACRE Chairman, KCC | June 2016 |
| 2 | ASC meetingAgree Project plan,  | SACRE | 15.6.16 |
| 3 | WG meeting Determine structure and agree aims and underpinning philosophy of syllabusAgree religions to be covered in different Key StagesIdentify interim tasks for sub groups* Primary & Secondary schools consultation
* Assessment
* Begin writing of syllabus
 | WG members | 11.7.16 |
| 4 | WG meetingReview of progressEmerging issuesNext steps to develop further:* Writing syllabus details for each key stage
* Identifying additional units of work as support materials
* Identify sections for inclusion in Non-statutory Guidance
 | WG members | 23.9.16 |
| 5 | ASCUpdate on progress since last ASCRequest Group 2 members identify contacts details for local faiths / places of worship for inclusion in syllabus.Seek agreement for developments so far | SACRE | 29.11.16 |
| 6 | WG Review of progressEmerging issuesNext steps to develop further:* Obtain Fore word statements – Diocese, KCC, SACRE Chairman
* Select illustrations for syllabus cover / internal
* Complete writing
* Proof reading Draft
 | WG members | 23.1.17 |

|  |  |  |  |
| --- | --- | --- | --- |
| 7 | ASC Update on progress since last ASCSeek agreement for developments so farConsult with schools on developing syllabus | SACRE | 7.3.17 |
| 8 | WGFinal review and agreement on syllabus | WG members | 26.5.17 |
| 9 | ASCFinal approval of SyllabusSend to KCC for final approval | SACRE | 1.6.17 |
| 10 | Publish to schools  | KCC | 1.9.17 |
| 11 | Fully implemented in Kent schools |  | 1.9.18 |
|  |  |  |  |
|  |  |  |  |