**Kent SACRE Agreed Syllabus Review**

**Project Plan 2016 - 2017**

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Activity** | **Lead Responsibility / Involvement** | **Completion Date** |
| 1 | Secure funding to complete review and publish web based KAS | SACRE Chairman, KCC | June 2016 |
| 2 | ASC meeting  Agree Project plan, | SACRE | 15.6.16 |
| 3 | WG meeting  Determine structure and agree aims and underpinning philosophy of syllabus  Agree religions to be covered in different Key Stages  Identify interim tasks for sub groups   * Primary & Secondary schools consultation * Assessment * Begin writing of syllabus | WG members | 11.7.16 |
| 4 | WG meeting  Review of progress  Emerging issues  Next steps to develop further:   * Writing syllabus details for each key stage * Identifying additional units of work as support materials * Identify sections for inclusion in Non-statutory Guidance | WG members | 23.9.16 |
| 5 | ASC  Update on progress since last ASC  Request Group 2 members identify contacts details for local faiths / places of worship for inclusion in syllabus.  Seek agreement for developments so far | SACRE | 29.11.16 |
| 6 | WG  Review of progress  Emerging issues  Next steps to develop further:   * Obtain Fore word statements – Diocese, KCC, SACRE Chairman * Select illustrations for syllabus cover / internal * Complete writing * Proof reading Draft | WG members | 23.1.17 |

|  |  |  |  |
| --- | --- | --- | --- |
| 7 | ASC  Update on progress since last ASC  Seek agreement for developments so far  Consult with schools on developing syllabus | SACRE | 7.3.17 |
| 8 | WG  Final review and agreement on syllabus | WG members | 26.5.17 |
| 9 | ASC  Final approval of Syllabus  Send to KCC for final approval | SACRE | 1.6.17 |
| 10 | Publish to schools | KCC | 1.9.17 |
| 11 | Fully implemented in Kent schools |  | 1.9.18 |
|  |  |  |  |
|  |  |  |  |